## Sheet1
LAUNCH
ROLE | TASK | 2018-01-12 | 2018-01-19 | 2018-01-26 | 2018-02-02 | 2018-02-09 | 2018-02-16 | 2018-02-23 | 2018-03-02 | 2018-03-09 | 2018-03-16 | 2018-03-23 | 2018-03-30 | 2018-04-06 | 2018-04-13 | 2018-04-20 | Hours / task |  | Adjusted 20%
Project Manager | Scope Testing | 1.5 | [14 empty] | 1.5
| Risk Management Plan | 0.5 | [14 empty] | 0.5
| Task List |  | 0.5 | -------------> | [12 empty] | 0.5
| Network graph |  | 1 | -------------> | [12 empty] | 1
| Resources plan |  | 0.25 | -------------- | [12 empty] | 0.25
| Gantt chart |  | 2 | -------------> | [12 empty] | 2
| Timeline |  |  | 0.5 | [12 empty] | 0.5
| Budget |  |  | 0.5 | [12 empty] | 0.5
| Estimate |  |  | 1.5 | [12 empty] | 1.5
| SEO keyword research |  |  |  | 2 | [11 empty] | 2
| SEO distribution chart |  |  |  |  | 1 | -------------- | -------------> | [8 empty] | 1
| Google analytics set-up | [7 empty] | <------------ | -------------- | -------------- | -------------- | 1 |  |  |  | 1
| Accessibility plan |  |  |  |  | 1.5 | -------------- | -------------> | [8 empty] | 1.5
| Quality Assurance plan |  |  |  |  | 1.5 | -------------- | -------------> | [8 empty] | 1.5
| Maintenance plan | [5 empty] | 1 | -------------> | [8 empty] | 1
| Post mortem prep | [5 empty] | 0.5 | -------------> | [8 empty] | 0.5
| Port mortem execute | [14 empty] | 2 | 2
| Domain name research | [7 empty] | <------------ | -------------- | -------------- | 2 |  |  |  |  | 2
| Hosting + domain | [11 empty] | 1 |  |  |  | 1
| Quality assurance testing | [13 empty] | 4 |  | 4
[17 empty] | 25.75 | PM TOTAL | 30.9
Copywriting | Bio | [7 empty] | 1 | -------------- | -------------> | [5 empty] | 1
| Project synopsis | [7 empty] | 2 | -------------- | -------------> | [5 empty] | 2
[17 empty] | 3 | CP TOTAL | 3.6
Development | Local dev environment | 1 | [14 empty] | 1
| Research wp/bootstrap/flex | <------------ | -------------- | -------------- | 4 | -------------- | -------------> | [9 empty] | 4
| Test wp/bootstrap/flex |  |  |  |  | <------------ | -------------- | 3 | -------------- | -------------> | [6 empty] | 3
| Code infrastructure | [9 empty] | <------------ | 4 |  |  |  |  | 4
| Site migration | [12 empty] | 0.5 |  |  | 0.5
| SEO Yoast plug-in | [7 empty] | <------------ | -------------- | -------------- | -------------- | 0.5 |  |  |  | 0.5
| Google analytics plug-in | [7 empty] | <------------ | -------------- | -------------- | -------------- | 0.5 |  |  |  | 0.5
| Research canvas | <------------ | -------------- | -------------- | 4 | -------------- | -------------> | [9 empty] | 4
| Test canvas |  |  |  |  | <------------ | -------------- | 4 | -------------- | -------------> | [6 empty] | 4
| Code canvas | [10 empty] | <------------ | 4 |  |  |  | 4
| Page loading icon | <------------ | -------------- | -------------- | -------------- | -------------- | -------------- | -------------- | -------------- | -------------- | -------------- | -------------- | 2 |  |  |  | 2 |  | 25%
[17 empty] | 27.5 | DEV TOTAL | 34.375
Design | Research Sketch | 3 | -------------- | -------------- | -------------> | [11 empty] | 3
| Research design systems | 3 | -------------- | -------------- | -------------> | [11 empty] | 3
| Style guide |  |  |  |  | <------------ | -------------- | 2 | [8 empty] | 2
| Design comps | [7 empty] | <------------ | -------------- | 8 | [5 empty] | 8
| Design comp alternatives | [7 empty] | <------------ | -------------- | 4 | [5 empty] | 4
[17 empty] | 20 | DES TOTAL | 24
| Hours / week | 9 | 3.75 | 2.5 | 10 | 4 | 1.5 | 9 | 3 | 0 | 12 | 6 | 9 | 0.5 | 4 | 2 | 76.25 | TOTAL | 93.125