## Sheet1
|  | Expression of Interest | Minimum Viable Product (MVP) | [6 empty] | TEST | Feature 1 |  | TEST | Feature 2 |  | TEST | Feature 3 |  | TEST | LAUNCH
ROLE | TASK | 2021-11-21 | 2020-01-04 | 2020-01-11 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15 | 2020-02-22 | 2020-02-29 | 2020-03-07 | 2020-03-14 | 2020-03-21 | 2020-03-28 | 2020-04-04 | 2020-04-11 | 2020-04-18 | 2020-04-25 | 2020-04-30 | Hours / task |  | Adjusted 15%-20%
Account Manager | Work-start meeting |  | 1 | [17 empty] | 1
| Research competition |  | <------------ | 3 | -------------> | [15 empty] | 3
| Design comp meeting |  |  |  | 2 | [15 empty] | 2
| MVP meeting | [8 empty] | 4 | [10 empty] | 4
| Feature 1 meeting | [11 empty] | 2 | [7 empty] | 2
| Feature 2 meeting | [14 empty] | 2 |  |  |  |  | 2
| Feature 3 meeting | [17 empty] | 2 |  | 2
| Launch meeting | [18 empty] | 4 | 4 |  | (+15%)
[21 empty] | 20 | AM TOTAL | 23
Project Manager | Scope Testing |  | 1.5 | [17 empty] | 1.5
| Risk Management Plan |  | 0.5 | [17 empty] | 0.5
| Task List | 0.5 |  |  | -------------> | [15 empty] | 0.5
| Resources plan |  |  | 0.25 | -------------- | [15 empty] | 0.25
| Gantt chart | 2 |  |  | -------------> | [15 empty] | 2
| Timeline | 0.5 | [18 empty] | 0.5
| Budget | 0.5 | [18 empty] | 0.5
| Estimate | 1.5 | [18 empty] | 1.5
| Accessibility plan | [5 empty] | 1.5 | -------------- | -------------> | [11 empty] | 1.5
| Quality Assurance plan | [5 empty] | 1.5 | -------------- | -------------> | [11 empty] | 1.5
| Maintenance plan | [6 empty] | 1 | -------------> | [11 empty] | 1
| Post mortem prep | [6 empty] | 0.5 | -------------> | [11 empty] | 0.5
| Port mortem execute | [15 empty] | 2 |  |  |  | 2
| Domain name research | [8 empty] | <------------ | -------------- | -------------- | 2 | [7 empty] | 2
| Hosting + domain | [12 empty] | 1 | [6 empty] | 1
| Quality assurance plan | [14 empty] | 4 |  |  |  |  | 4 |  | (+15%)
[21 empty] | 20.75 | PM TOTAL | 23.8625
Content Writer | Content Writing |  | <------------ | -------------- | -------------- | 4 | -------------- | -------------> |  | 3 | -------------- | -------------> | [8 empty] | 7
| Marketing plan | [8 empty] | 12 | -------------- | -------------> | [8 empty] | 12
| SEO keyword research |  |  |  |  | 6 | [14 empty] | 6 | 5252
| SEO distribution chart | [5 empty] | 2 | -------------- | -------------> | [11 empty] | 2
| Google analytics set-up | [8 empty] | <------------ | -------------- | -------------- | -------------- | 1 | [6 empty] | 1
| Marketing implementation | [15 empty] | <------------ | -------------- | -------------- | 12 | 12 |  | (+15%)
[21 empty] | 40 | CW TOTAL | 46
UX Designer | Interview users | 4 | [18 empty] | 4
| Develop user personas | 3 | [18 empty] | 3
| Need statement | 1 | [18 empty] | 1
| Big idea | 3 | [18 empty] | 3
| Features | [19 empty] | 0
| Customer Journey Map |  | 2 | [17 empty] | 2
| Site map |  | 3 | [17 empty] | 3
| Low Fidelity Wireframes |  |  | 6 | [16 empty] | 6
| Prototype test | [5 empty] | 5 | [13 empty] | 5
| MVP test plan | [5 empty] | <------------ | 3 | [12 empty] | 3
| MVP test | [8 empty] | 5 | [10 empty] | 5
| Feature test plans | [9 empty] | 2 |  |  | 2 |  |  | 2 |  |  |  | 6
| Feature tests | [11 empty] | 5 |  |  | 5 |  |  | 5 |  | 15
| Documentation / reports | [18 empty] | 4 | 4 |  | (+15%)
[21 empty] | 60 | UX TOTAL | 69
Designer | Moodboard |  | 3 | [17 empty] | 3
| Logo - primary + secondary |  |  | 9 | [16 empty] | 9
| High fidelity wireframes |  |  | <------------ | 6 | -------------> | [14 empty] | 6
| Style guide |  |  |  | <------------ | 4.5 | [14 empty] | 4.5
| Design system |  |  |  |  | <------------ | 9 | -------------> | [12 empty] | 9
| Prototype |  |  |  | <------------ | 12 | [14 empty] | 12
| Assets |  |  |  |  | <------------ | -------------- | 12 | -------------> | [11 empty] | 12
| Social Media Posts | [9 empty] | 6 | -------------- | -------------> | [7 empty] | 6
| Ads | [11 empty] | 8 | -------------- | -------------> | [5 empty] | 8
| Promo video | [11 empty] | <------------ | 23 | -------------- | -------------> |  |  |  |  | 23 |  | (+20%)
[21 empty] | 92.5 | DES TOTAL | 111
Developer | Research tech specs |  | 6.5 | [17 empty] | 6.5
| Set up dev environment |  | 2 | [17 empty] | 2
| Code infrastructure |  |  | 7 | [16 empty] | 7
| Coding | [5 empty] | 35 | -------------- | -------------> |  | <------------ | 23 |  | <------------ | 16 |  | <------------ | 11 |  |  | 85
| SEO implementation |  |  |  | 2 | [15 empty] | 2
| Quality Assurance | [7 empty] | 4 | [9 empty] | 8 |  | 12 |  | (+20%)
[21 empty] | 114.5 | DEV TOTAL | 137.4
TOTAL |  | 16 | 19.5 | 25.25 | 10 | 26.5 | 54 | 16.5 | 4 | 24 | 8 | 23 | 17 | 27 | 16 | 11 | 4 | 11 | 15 | 20 | 347.75 |  | 410.2625